## Sheet1
Task Description | Predicted Time | Actual Time | Start Date | Start Time | End Date | End Time | Comments | Diff | Status
Build Time Tracking Sheet | 20 | 62 | 2023-01-17 | 8:55 | 2023-01-17 | 9:57 | N/A | 42 | 1
Fix AdultCowsWithCalvesAtmosphericDepositionN2O | 60 | 22 | 2023-01-17 | 10:44 | 2023-01-17 | 11:06 | N/A | -38 | 1
Fix API app.js file so that chart.js is showing data | 40 | 133 | 2023-01-17 | 11:13 | 2023-01-17 | 13:26 | N/A | 93
log auth code, access token, raw data to the console | 10 | 30 | 2023-01-17 | 12:26 | 2023-01-17 | 12:57 | N/A | 20
Fix x axes | 45 | 47 | 2023-01-17 | 14:10 | 2023-01-17 | 14:57 | N/A | 2
get axes for Rob's additional charts | 60 | 62 | 2023-01-17 | 13:55 | 2023-01-17 | 14:57 | N/A | 2
Build Yield x Variety Chart | 80 | 565 | 2023-01-19 | 9:25 | 2023-01-20 | 10:50 | N/A | 485 | 1
Build fertiliser/urea emmissions for each paddock chart | 60 | 59 | 2023-01-23 | 12:59 | 2023-01-23 | 13:58 | N/A | -1
Hunt down Hilary's Measure Schema bug | 10 | 75 | 2023-01-18 | 9:46 | 2023-01-18 | 11:02 | N/A | 65
Fix Time Tracker to track over multiple days | 45 | 20 | 2023-01-20 | 10:51 | 2023-01-20 | 11:11 | N/A | -25
Fix Yield x Variety charts to average and group varieties that are the same | 60 | 56 | 2023-01-20 | 12:23 | 2023-01-20 | 13:19 | N/A | -4 | 1
Find endpoint for fuel used on API | 45 | 0 |  |  |  |  | N/A | -45
Build function to fetch fuel per paddock data |  | 0 |  |  |  |  | N/A | 0
build function to do Scope1 fuel carbon calculation |  | 0 |  |  |  |  | N/A | 0
Build fuel emissions per paddock chart |  | 0 |  |  |  |  | N/A | 0
Build function to get all of the urea spread operations and return the urea applied per ha for each paddock | 80 | 86 | 2023-01-23 | 10:28 | 2023-01-23 | 11:55 | N/A | 6
Build function to calculate scope1 urea emissions | 45 | 14 | 2023-01-23 | 12:43 | 2023-01-23 | 12:58 | N/A | -31
Include the name of fields in the urea chart | 30 | 42 | 2023-01-23 | 14:04 | 2023-01-23 | 14:46 | N/A | 12 | 0
SELECT statement that gets yield per ha for crops in agzones | 30 | 19 | 2023-01-23 | 15:09 | 2023-01-23 | 15:28 | N/A | -11
switch from harvest date to sowing date | 45 | 499 | 2023-01-24 | 14:00 | 2023-01-25 | 14:20 | N/A | 454 | 0
Add pausability to Time Tracker | 35 | 0 |  |  |  |  | N/A | -35
make a graph for 2022 and 2021 season for yield x seed date | 120 | 380 | 2023-01-27 | 9:30 | 2023-01-27 | 15:50 | N/A | 260
only show canola on yield x seed | 45 | 0 |  |  |  |  | N/A | -45
add sorting to columns to questionnaire files tile on profit series |  | 0 |  |  |  |  | N/A | 0
Separate yield x seed date into charts for each croptype | 120 | 26 | 2023-02-01 | 13:09 | 2023-02-01 | 13:36 | N/A | -94
add trendline to graphs | 120 | 20 | 2023-02-01 | 13:51 | 2023-02-01 | 14:11 | N/A | -100
remove outlier data | 30 | 53 | 2023-02-01 | 14:19 | 2023-02-01 | 15:12 | N/A | 23
get urea chart working | 90 | 592 | 2023-02-02 | 5:40 | 2023-02-02 | 15:32 | N/A | 502
Clean edit-questionnaire-sidebar file | 180 | 3562 | 2023-02-07 | 11:08 | 2023-02-14 | 14:30 | N/A | 3382
Fix "Next" button bug in carbon sections | 240 | 185 | 2023-02-15 | 11:25 | 2023-02-15 | 14:30 | N/A | -55
Compile all of the inputs required for carbon complete | 420 | 436 | 2023-02-15 | 15:44 | 2023-02-16 | 15:00 | N/A | 16
Test new carbon calcs | 140 | 236 | 2023-02-21 | 11:34 | 2023-02-21 | 15:30 | N/A | 96
build enterprise bootstrap table template | 180 | 37 | 2023-02-22 | 11:08 | 2023-02-22 | 11:45 | N/A | -143
Port all of the new carbon calcs over to carbon calc 2 measure schema | 180 | 204 | 2023-03-03 | 12:06 | 2023-03-03 | 15:30 | N/A | 24
port all the carbon calcs correctly this time | 180 | 126 | 2023-03-07 | 10:54 | 2023-03-07 | 13:00 | N/A | -54
sort out measure schemas into folders | 60 | 56 | 2023-03-07 | 13:18 | 2023-03-07 | 14:14 | N/A | -4
create new schema which includes carbon changes and hilary's changes | 300 | -21597017 | 2023-03-07 | 14:17 |  |  | N/A | -21597317 | 0
Scope1 carbon calcs testing | 180 | -21604215 | 2023-03-21 | 22:15 |  |  | N/A | -21604395
Separate yield x seed date into charts for each croptype |  | 0 |  |  |  |  | N/A | 0
add pasture seed crop |  | 0 |  |  |  |  | N/A | 0
add irrigated version of each crop enterprise |  | 0 |  |  |  |  | N/A | 0
create crop selection tables (separate into summer and winter) |  | 0 |  |  |  |  | N/A | 0
replace PaidCurrentYearForLastYear system with PaymentAdjustment (Use PaidNextYearForCurrentYear measure) (put explanation above table to specify when to use positive or negative) |  | 0 |  |  |  |  | N/A | 0
add payment adjustment measures to remaining |  | 0 |  |  |  |  | N/A | 0
fix fertiliser used | 240 | -21607876 | 2023-03-30 | 11:16 |  |  | N/A | -21608116
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0
placeholder |  | 0 |  |  |  |  | N/A | 0